## Gantt Chart (Construction)
Project Name:
Task Name | Start (Date) | End (Date) | Duration (Days) | Priority | Percentage of Completion
Excavate site | 2025-04-02 | 2025-04-30 | 28 | High | 0%
Pile Foundation | 2025-05-04 | 2025-05-20 | 16 | High | 50%
Foundation Testing | 2025-05-21 | 2025-05-29 | 8 | Medium | 100%
Install floors and walls | 2025-05-30 | 2025-06-16 | 17 | High | 30%
Install plumbing fixtures | 2025-06-18 | 2025-06-30 | 12 | High | 60%